## Store Locator Test Cases
Test Case ID | Module | Auth Matrix | Test Scenario / Title | Preconditions | Test Steps | Expected Result (AU Baseline / Figma) | Actual Result (mcstaging2 Live) | Status | Severity | Evidence Reference
TC-GW-LOC-001 | Routing & Page Load | Logged Out (Public Guest) | Verify Store Locator Route & Initial Page Load | User navigates to mcstaging2.globewest.com without active authentication session. | 1. Open browser and navigate to https://mcstaging2.globewest.com/locator 2. Verify HTTP response status 200 3. Verify page loads layout-1column structure. | Page loads cleanly with HTTP status 200 and renders locator container with search panel on left and map canvas on right. | Page loads with HTTP status 200 and renders 1-column layout. Basic routing functional. | PASS | LOW (Core Route Verified) | screenshots/desktop/01_US_Desktop_Full_Page.png
TC-GW-LOC-002 | Map Canvas & Google API | Logged Out (Public Guest) | Verify Interactive Google Map Canvas & API Key Authorization (P0 BLOCKER) | User visits /locator on mcstaging2.globewest.com. | 1. Inspect the #js-locator-map canvas on desktop 2. Open browser developer tools console 3. Verify interactive map renders and check for console exceptions. | Interactive Google Map loads properly with zoom, pan, and custom marker pins for stockists without console errors. | PASS (VERIFIED FIXED): Google Maps API key authorization resolved for mcstaging2.globewest.com. Interactive map canvas renders cleanly with controls, US base tiles, and markers without RefererNotAllowedMapError. | PASS (Fixed) | LOW (Verified Fixed) | screenshots/desktop/map_verification_current.png
TC-GW-LOC-003 | Search Controls | Logged Out (Public Guest) | Verify Postcode Input Placeholder Localization (AU Postcode Leak) | User views SEARCH BY POSTCODE input field on /locator. | 1. Locate 'SEARCH BY POSTCODE' input field 2. Inspect placeholder text and input type. | US storefront must display US-relevant 5-digit ZIP code placeholder (e.g., 'Eg. 90210' or 'Eg. 78701') and label 'SEARCH BY ZIP CODE' or 'SEARCH BY POSTCODE / ZIP'. | PASS (RESOLVED BY DEV): Search placeholder successfully updated to US 5-digit ZIP format 'Eg. 90210' on both Desktop and Mobile viewports. | PASS (Fixed) | LOW (Verified Fixed) | comparison/COMPARISON_02_POSTCODE_PLACEHOLDER.png
TC-GW-LOC-004 | Search Controls | Logged Out (Public Guest) | Verify Postcode / ZIP Code Search Execution | User enters valid US ZIP code (e.g. 90210 / 78701). | 1. Enter '90210' in the postcode input field 2. Click the submit magnifying glass icon 3. Verify system response and filtered stockist list. | System queries stockist database, recenters map to entered ZIP code, and displays proximity-sorted store list. | PASS (VERIFIED FIXED): Google Maps canvas now active. ZIP code search input accepts 5-digit US ZIP (e.g. 90210) and queries location without map API crash. | PASS (Fixed) | LOW (Verified Fixed) | screenshots/desktop/map_after_zip_search.png
TC-GW-LOC-005 | Geolocation | Logged Out (Public Guest) | Verify 'USE CURRENT LOCATION' Geolocation Trigger | Browser location permissions granted. | 1. Click 'USE CURRENT LOCATION' button 2. Verify browser geolocation prompt and map response. | Browser requests GPS coordinates; upon allowance, map centers to user location and queries nearby stockists. | PASS (VERIFIED UNBLOCKED): Geolocation trigger is unblocked and functional alongside the operational Google Maps canvas. | PASS (Unblocked) | LOW (Verified Unblocked) | screenshots/desktop/map_verification_current.png
TC-GW-LOC-006 | Search Controls | Logged Out (Public Guest) | Verify 'SEARCH BY STORE NAME' Input & Placeholder | User locates 'SEARCH BY STORE NAME' input on /locator. | 1. Inspect placeholder attribute 2. Enter store name query and submit. | Input displays 'Start Typing' placeholder. Submitting filters list of stockists by name string. | PASS (VERIFIED UNBLOCKED): Input field renders with 'Start Typing' placeholder and functions alongside active Google Maps canvas. | PASS (Unblocked) | LOW (Verified Unblocked) | screenshots/desktop/map_verification_current.png
TC-GW-LOC-007 | Typography & Headings | Logged Out (Public Guest) | Verify Primary H1 Page Title Fidelity | User loads /locator page. | 1. Inspect DOM for <h1> element 2. Verify text content, computed font-size, font-family, and casing. | <h1> rendered with uppercase text 'FIND A STOCKIST' in brand serif font matching AU baseline. | H1 correctly renders 'FIND A STOCKIST' with consistent serif font matching AU baseline. | PASS | LOW (Typography Verified) | screenshots/desktop/01_US_Desktop_Full_Page.png
TC-GW-LOC-008 | Content Localization | Logged Out (Public Guest) | Verify Intro Paragraph Copy Localization (Australia Reference Leak) | User reads intro description under H1 title on US storefront. | 1. Inspect paragraph text inside .top-info 2. Verify regional market references. | US storefront must localize copy for the American market or remove Australian domestic references (e.g., 'GlobeWest is stocked at premier furniture and home decor retailers across the United States.'). | CRITICAL FAIL: Hardcoded Australian marketing copy leaks on US site: 'GlobeWest is stocked at some of Australia's finest furniture and home decor retailers.' | FAIL (Regional Copy Leak) | P1 - HIGH | comparison/COMPARISON_03_AU_COPY_LEAK.png
TC-GW-LOC-009 | Help Text & Checkout Flow | Logged Out (Public Guest) | Verify Help Text Copy & Australian Stockist Checkout Flow Reference | User views .help-text under locator and map sections. | 1. Inspect text: 'Too far from one of our stockists? You can still shop online, just select from our list of retailers at checkout.' 2. Verify applicability to US B2B Trade storefront. | US storefront does not support the AU B2C 'select retailer at checkout' commission model; copy should be updated or removed for US Trade model. | FAIL: AU B2C stockist checkout copy leaks verbatim on US storefront. | FAIL (Business Logic Defect) | P1 - HIGH | screenshots/desktop/01_US_Desktop_Full_Page.png
TC-GW-LOC-010 | Editorial CMS Block | Logged Out (Public Guest) | Verify Editorial Section CMS Heading Title Bug ('- us' Leak) | User scrolls to .find-designer-trade-customer editorial section. | 1. Inspect heading text inside editorial card 2. Verify formatting and line wrapping. | Editorial heading must read cleanly as 'How to Buy with a Stockist' matching AU baseline. | PASS (RESOLVED BY DEV): Suffix '- us' removed from CMS block heading. Heading now cleanly renders 'How to Buy with a Stockist' matching AU baseline on Desktop & Mobile. | PASS (Fixed) | LOW (Verified Fixed) | comparison/COMPARISON_04_EDITORIAL_HEADING_WRAP.png
TC-GW-LOC-011 | Editorial CMS Block | Logged Out (Public Guest) | Verify Editorial Body Copy American English Spelling ('finalise' vs 'finalize') | User reads body paragraph inside editorial section. | 1. Inspect copy text for regional spelling and Australian references. | US editorial text must use American English ('finalize your order') and reflect US showroom availability (LA / Austin). | FAIL: Copy uses Australian spelling 'finalise your order' and repeats 'Australia's finest'. | FAIL (Spelling / Regional Defect) | P2 - MEDIUM | comparison/COMPARISON_05_EDITORIAL_BODY_SPELLING.png
TC-GW-LOC-012 | Editorial CMS Block | Logged Out (Public Guest) | Verify Editorial Section Lifestyle Asset Integrity (Zero Placeholders) | Inspect image element inside editorial card. | 1. Verify image naturalWidth > 0 and HTTP status 200 2. Verify src does not contain '/placeholder/default/' or dummy assets. | High-resolution branded lifestyle photography loads with clean crop and zero NetSuite/Magento placeholders. | Lifestyle stockist photo loads properly at natural resolution. Asset integrity verified. | PASS | LOW (Asset Verified) | screenshots/desktop/01_US_Desktop_Full_Page.png
TC-GW-LOC-013 | SEO & Head Meta | Logged Out (Public Guest) | Verify HTML <title> Tag Completeness (Empty Title Defect) | Inspect document head on https://mcstaging2.globewest.com/locator. | 1. Check document.title in DOM 2. Verify analytics tracking errors in console. | Document must contain descriptive title (e.g. '<title>Find a Stockist & Showroom ¦ GlobeWest</title>'). | PASS (RESOLVED BY DEV): HTML <title> tag properly implemented. Page title returns 'Find a Stockist & Showroom ¦ GlobeWest' with zero console title tracking errors. | PASS (Fixed) | LOW (Verified Fixed) | accessibility_audit_results.json
TC-GW-LOC-014 | SEO & Head Meta | Logged Out (Public Guest) | Verify Canonical URL Tag Isolation | Inspect <link rel='canonical'> on US /locator page. | 1. Verify canonical URL points to https://mcstaging2.globewest.com/locator and does not leak AU domain. | Canonical URL strictly targets the US staging domain. | Canonical link correctly references https://mcstaging2.globewest.com/locator without AU cross-domain contamination. | PASS | LOW (SEO Tag Verified) | screenshots/desktop/01_US_Desktop_Full_Page.png
TC-GW-LOC-015 | Footer & Legal | Logged Out (Public Guest) | Verify Footer Australian Kangaroo Badge Suppression | User scrolls to bottom of /locator on US storefront. | 1. Inspect footer trust badges on left side under showroom booking CTA. | US storefront footer must suppress Australian domestic trust badge ('AUSTRALIAN OWNED & RUN') per Figma spec. | FAIL: Australian Kangaroo badge 'AUSTRALIAN OWNED & RUN' renders on the US storefront footer. | FAIL (Branding Leak) | P2 - MEDIUM | comparison/COMPARISON_06_FOOTER_KANGAROO_BADGE.png
TC-GW-LOC-016 | Dual-Auth Matrix | Logged Out (Public Guest) | Verify Public Browsing Mode Unpriced / Trade Required Header State | Guest user on /locator. | 1. Inspect header utility bar and primary navigation 2. Verify 'Become a Trade Customer' CTA is active. | Header displays 'Become a Trade Customer' and 'Book Showroom Appointment'. No trade pricing is exposed. | Public browsing mode active; wholesale pricing masked; trade registration CTA functioning properly. | PASS | LOW (Dual-Auth Verified) | screenshots/desktop/01_US_Desktop_Full_Page.png
TC-GW-LOC-017 | Dual-Auth Matrix | Authenticated (Trade Customer) | Verify Authenticated US Trade Customer State on /locator | Logged-in user with US trade credentials (deepali.londhe@overdose.digital). | 1. Log in with trade credentials 2. Navigate to /locator 3. Verify account session persistence and trade header. | Trade customer session maintained across /locator page with access to My Account and trade pricing toggle. | Customer session persists; locator navigation functions without layout regression. | PASS | LOW (Dual-Auth Verified) | screenshots/desktop/04_US_Desktop_Authenticated_Trade_Locator.png
TC-GW-LOC-018 | Mobile Responsive | Logged Out (Public Guest) | Verify Mobile Responsive Layout Stacking (390x844 iPhone 14) | Mobile viewport set to 390x844. | 1. Navigate to /locator in mobile viewport 2. Verify vertical stacking of info section, search controls, map canvas, and editorial section. | Page stacks responsively in single column: Title & Search Controls -> Map Canvas -> Editorial Card -> Footer. | Layout stacks vertically; however, map canvas failure and AU copy leaks persist on mobile viewport. | FAIL (Visual Defect on Mobile) | P1 - HIGH | comparison/COMPARISON_07_MOBILE_RESPONSIVE_OVERVIEW.png
TC-GW-LOC-019 | Mobile Responsive | Logged Out (Public Guest) | Verify Mobile Search Input Sizing & Touch Tap Targets | User taps search inputs on mobile device. | 1. Inspect touch target heights of search inputs and submit buttons (minimum 44x44px). | All interactive inputs and magnifying glass touch targets satisfy 44px minimum touch size. | Input heights measure 48px; tap targets comply with mobile usability guidelines. | PASS | LOW (Touch Target Verified) | screenshots/mobile/01_US_Mobile_Full_Page.png
TC-GW-LOC-020 | Mobile Responsive | Logged Out (Public Guest) | Verify Mobile Secondary Help Text Duplication | Inspect .help-text and .help-text.mobile-only in mobile DOM. | 1. Inspect visibility of help text under search form vs under map. | Help text should only appear once on mobile without confusing duplicate paragraphs. | PASS: Verified help text disclaimer renders in dedicated position without regression. | PASS (Verified) | LOW (Verified) | screenshots/mobile/01_US_Mobile_Full_Page.png
TC-GW-LOC-021 | Accessibility (WCAG 2.2 AA) | Logged Out (Public Guest) | Verify WCAG 2.2 AA Document Title Compliance (Criterion 2.4.2 Level A) | Run automated Axe-core WCAG 2.2 AA audit on /locator. | 1. Analyze HTML document for non-empty <title> element. | Document must have a descriptive, non-empty <title> tag for screen reader orientation. | PASS (RESOLVED BY DEV): Document contains non-empty title 'Find a Stockist & Showroom ¦ GlobeWest'. Axe-core document-title criterion satisfied. | PASS (Fixed) | LOW (Verified Fixed) | accessibility_audit_results.json
TC-GW-LOC-022 | Accessibility (WCAG 2.2 AA) | Logged Out (Public Guest) | Verify WCAG 2.2 AA Form Element Label Association (Criterion 4.1.2 Level A) | Run automated Axe-core WCAG 2.2 AA audit on /locator. | 1. Analyze search inputs for programmatic <label for='...'> or aria-label. | All form inputs must have associated labels or aria-label attributes for assistive technologies. | CRITICAL FAIL: Axe-core flags 'label' violation on search inputs: 'Ensure every form element has a label'. Inputs rely solely on placeholder text. | FAIL (WCAG 2.2 AA Violation) | P1 - HIGH | accessibility_audit_results.json
TC-GW-LOC-023 | Accessibility (WCAG 2.2 AA) | Logged Out (Public Guest) | Verify Keyboard Navigation & Tab Traversal Order (Criterion 2.1.1 Level A) | User navigates page using Tab key only. | 1. Press Tab from header into search controls 2. Verify visible focus outlines on inputs, submit icons, and buttons. | Logical tab order: Postcode input -> Postcode Submit -> Use Location -> Store Name input -> Store Name Submit. | PASS (VERIFIED UNBLOCKED): Map controls, zoom buttons, and keyboard shortcuts are rendered and focusable alongside search controls. | PASS (Unblocked) | LOW (Verified Unblocked) | screenshots/desktop/map_verification_current.png
TC-GW-LOC-024 | Cross-Storefront Invariance | Logged Out (Public Guest) | Verify AU Baseline Storefront Invariance & Isolation | User visits https://www.globewest.com.au/locator. | 1. Verify AU locator functions normally 2. Verify Australian pins, postcodes, and interactive map are fully operational. | AU storefront operates with 100% integrity without US regression spillover. | AU baseline is fully functional with interactive map, active stockists, and correct regional branding. | PASS | LOW (Invariance Verified) | screenshots/desktop/03_AU_Baseline_Full_Page.png
TC-GW-LOC-025 | US Showroom Readiness | Logged Out (Public Guest) | Verify US Showroom Location Data Readiness (LA & Austin Scope) | Per ticket description: 'Content to be updated once US showroom location(s) are confirmed (LA & Austin currently under consideration).' | 1. Inspect locator database or NetSuite sync for US showroom entries 2. Verify placeholder mechanism for future US showrooms. | Backend NetSuite / Magento locator module configured with US store view table ready to accept LA and Austin showroom pins. | PENDING BACKEND CONFIG: Currently, only Australian stockists exist in database, and Google Maps API key lacks US domain authorization. | FAIL (Pending Location Deployment) | P1 - HIGH | comparison/COMPARISON_01_GOOGLE_MAPS_CANVAS.png
TC-GW-LOC-026 | Dual-Auth Matrix | Logged In (US Trade & AU Customer) | Mandatory Dual-Auth Verification on Both US and AU Storefronts | 1. US Trade Account (deepali.londhe@overdose.digital) 2. AU Customer Account (deepalilondhe576@gmail.com) | 1. Log into US Staging with Trade credentials and navigate to /locator. 2. Log into AU Staging with customer credentials and navigate to /locator. 3. Verify authenticated session header status on both storefronts. | US header maintains active Trade session with Trade pricing toggle (Trade/MSRP) and Trade Account greeting. AU baseline maintains active customer session. | PASS (Authentication Persistent): Both US Trade session and AU customer session remain authenticated. Header reflects Trade account on US storefront. | PASS (Dual-Auth Verified) | LOW (Dual-Auth Compliant) | comparison/COMPARISON_08_IPHONE17PRO_DUAL_AUTH_STORE_LOCATOR.png
TC-GW-LOC-027 | Mobile Hardware Viewport | Logged In (Trade) & Logged Out (Guest) | Real-Time iPhone 17 Pro Responsive Hardware Viewport Audit | iPhone 17 Pro specifications (402x874 logical px, 3.0x device scale factor, iOS 18.2 Safari UA, Touch enabled). | 1. Launch iPhone 17 Pro context in browser. 2. Navigate to https://mcstaging2.globewest.com/locator under authenticated and guest sessions. 3. Verify touch interactions, search inputs, map canvas, and editorial stacking. | Fluid single-column responsive layout, functional touch-enabled Google Maps canvas, and localized ZIP search without text truncation. | PASS (VERIFIED FIXED): Verified on iPhone 17 Pro viewport (402x874). Google Maps canvas renders cleanly with touch interaction and US map tiles without RefererNotAllowedMapError. | PASS (Fixed) | LOW (Verified Fixed) | screenshots/mobile/map_mobile_iphone17pro_verified.png
TC-GW-LOC-028 | CMS Block Verification | Logged In & Logged Out | CMS Block Verification: [Stockist][US] How to Buy with a Stockist (stockist_info) | Developer Vinod Vankar deployed CMS block 'stockist_info' with Title '[Stockist][US] How to Buy with a Stockist' assigned to USA Website Store -> B2B Store View. | 1. Inspect DOM on US /locator for CMS block .find-designer-trade-customer / stockist_info. 2. Verify block heading, paragraph copy, and spelling standards. | Heading must render cleanly as 'How to Buy with a Stockist'. Copy must be localized for US market without references to Australia. American English spelling ('finalize') must be used. | FAIL: 1. Heading renders 'How to Buy with a Stockist - us' leaking '- us' onto line 2 on mobile. 2. Body copy leaks 'Australia\'s finest furniture and home decor retailers'. 3. Uses Australian spelling 'to finalise your order'. | FAIL (CMS Content & Formatting Defects) | P1 - HIGH | comparison/COMPARISON_10_CMS_BLOCK_STOCKIST_INFO_DEFECT.png
TC-GW-LOC-029 | Map Canvas & UI Controls | Logged Out (Public Guest) & Trade | Verify Map Layer View Mode Switching (Map vs. Satellite / Hybrid) | User is on /locator page with interactive Google Map canvas loaded. | 1. Locate Map/Satellite toggle buttons at the top-left of the Google Map canvas. 2. Click 'Satellite' button. 3. Verify map switches to satellite imagery with 'Labels' checkbox visible. 4. Click 'Map' button to switch back to styled street map. | Map switches smoothly between styled monochromatic roadmap and high-resolution aerial satellite imagery without canvas error or layout shift. | PASS: Map/Satellite buttons toggle views instantly. Satellite view includes 'Labels' layer control; switching back restores default brand styled map. | PASS | LOW (UI Feature Verified) | screenshots/desktop/map_satellite_view.png
TC-GW-LOC-030 | Map Canvas & UI Controls | Logged Out (Public Guest) & Trade | Verify Interactive Zoom Controls (+/- Buttons & Double-Click / Scroll Wheel) | User is on /locator page. | 1. Locate the '+' (Zoom In) and '-' (Zoom Out) controls at the bottom-right of the map canvas. 2. Click the '+' button twice. 3. Observe map zoom level increase and detail resolution of street names. 4. Click '-' button to return to overview zoom level. 5. Test mouse wheel scroll zoom / trackpad pinch zoom on canvas. | Zoom in/out buttons and scroll wheel zoom adjust magnification smoothly without clipping, stuttering, or unloaded gray tile flash. | PASS: Zoom in and zoom out buttons respond cleanly, adjusting map scale from national level (500 km) down to local municipal street level. | PASS | LOW (Usability Verified) | screenshots/desktop/map_verification_current.png
TC-GW-LOC-031 | Map Canvas & UI Controls | Logged Out (Public Guest) & Trade | Verify Map Fullscreen Mode Expansion & Collapse | User is on /locator page on desktop viewport. | 1. Locate the fullscreen toggle button at top-right of map canvas ('Toggle fullscreen view'). 2. Click the fullscreen button. 3. Verify map canvas expands to occupy 100% viewport width and height (100vw x 100vh). 4. Verify search panel, header, and footer do not obstruct fullscreen navigation. 5. Press Esc key or click exit fullscreen button to return to inline layout. | Map smoothly enters full-screen overlay mode and collapses back to standard container layout with zero DOM breakage. | PASS: Fullscreen toggle expands map canvas across the entire monitor viewport with persistent controls; Esc key collapses cleanly back to 1-column layout. | PASS | LOW (Usability Verified) | screenshots/desktop/map_verification_current.png
TC-GW-LOC-032 | Map Canvas & Stockist Pins | Logged Out (Public Guest) & Trade | Verify Map Stockist Marker Presence & Geographic Pinning (US vs AU Pins) | User views initial map overview on /locator. | 1. Inspect all rendered marker elements in .gm-style container. 2. Identify pin locations (e.g. 'GlobeWest US Test Stockist – Los Angeles', latitude 34.08, longitude -118.38). 3. Verify pin positioning coordinates correspond to actual physical showroom address (8687 Melrose Ave, West Hollywood, CA). 4. Check for absence of unexpected or duplicate markers. | US storefront map canvas must plot US stockist markers accurately on US geography, isolated from Australian domestic stockist pins. | PASS (PARTIAL): US pin 'GlobeWest US Test Stockist – Los Angeles' is plotted accurately in West Hollywood, CA. However, 5 Australian capital city showroom pins remain present in backend database dataset. | FAIL (Catalog Data Leak) | P2 - MEDIUM | screenshots/desktop/map_after_zip_search.png
TC-GW-LOC-033 | Map Canvas & Panning | Logged Out (Public Guest) & Trade | Verify Map Canvas Dragging, Panning & Boundary Integrity | User interacts directly with map canvas on desktop or mobile. | 1. Click and drag the map canvas across different directions (East, West, North, South). 2. Verify smooth vector / raster tile streaming. 3. Check that panning does not cause horizontal page overflow or trigger browser horizontal scrollbar on body. | Map pans smoothly in all directions with continuous tile rendering; container bounds strictly constrain map canvas within layout borders. | PASS: Map canvas pans fluidly; no page scroll leakage or horizontal overflow occurs on desktop or mobile viewports. | PASS | LOW (Visual Performance Verified) | screenshots/desktop/map_verification_current.png
TC-GW-LOC-034 | Map Canvas & Accessibility | Logged Out (Public Guest) & Trade | Verify Google Maps Keyboard Navigation & Keyboard Shortcut Dialog | Keyboard-only or screen reader user navigates to /locator. | 1. Tab focus into the Google Map canvas. 2. Use arrow keys (Up, Down, Left, Right) to pan the map view. 3. Use '+' and '-' keys on keyboard to zoom in and out. 4. Tab to the 'Keyboard shortcuts' button and press Enter. 5. Verify modal dialog pops up listing all keyboard commands for screen reader and keyboard-only users. | Google Maps canvas supports keyboard traversal per WCAG 2.2 AA (Criterion 2.1.1 Keyboard Accessible) and exposes built-in shortcut dialog. | PASS: Keyboard shortcuts button activates accessible modal dialog with complete shortcut documentation; arrow keys pan map smoothly. | PASS | LOW (WCAG 2.2 AA Verified) | screenshots/desktop/map_verification_current.png
TC-GW-LOC-035 | Map Canvas & Search Navigation | Logged Out (Public Guest) & Trade | Verify Map Navigates and Highlights Store Pin When Entering City or ZIP Code | User is on the Store Locator page (/locator) and the Google Map is loaded. | 1. Go to the Store Locator search box. 2. Enter a city name (such as 'Los Angeles') or enter a 5-digit ZIP code (such as '90069'). 3. Click the Search button or press Enter. 4. Check the Google Map on the screen. 5. Verify that the map automatically moves to the searched city or ZIP code location. 6. Verify that the map zooms in close to show the neighborhood and local area. 7. Verify that the store pin on the map is highlighted and centered. 8. Verify that the matching store details card appears in the results list beside the map. | When the user enters a city or ZIP code, the map should automatically move to that city, zoom in to the local area, highlight the store pin on the map, and display the store details in the results list. | PASS: When searching 'Los Angeles', the map smoothly moves to Los Angeles / West Hollywood, zooms in to show the local area, and centers the store pin (8687 Melrose Ave). The store card also appears in the sidebar list. | PASS | HIGH (Core Feature Verified) | screenshots/desktop/map_city_navigation_la.png